## Plan
Kestrel and Co. Website - Analytics Implementation Plan - Phase 1
No | Activity | Owner | Deliverable | Start | End | Hours | Status
1 | Discovery workshop with business, ecommerce and marketing | Analytics team, Kestrel business team | Requirement notes | 02 Mar | 03 Mar | 12 | Done
2 | Draft the business requirements | Analytics team | BRD version 1.0 draft | 04 Mar | 09 Mar | 16 | Done
3 | Review and prioritise, agree phases | Analytics team, Kestrel business team |  | 10 Mar | 13 Mar | 8 | Done
4 | Sign off the BRD | Kestrel business team | BRD version 1.0 signed | 16 Mar | 16 Mar | 2 | Done
5 | Design the solution | Analytics team | SDR version 1.0 | 17 Mar | 20 Mar | 24 | Done
6 | SDR review and revisions | Analytics team, Kestrel business team | SDR version 1.2 | 23 Mar | 09 Apr | 12 | Done
7 | Sign off the SDR | Kestrel business team | SDR version 1.2 signed | 14 Apr | 14 Apr | 2 | Done
8 | Extend the SDR into technical instructions | Analytics team | TSD version 1.0 | 15 Apr | 16 Apr | 20 | Done
9 | Walkthrough with the development team | Analytics team, Kestrel web dev |  | 11 May | 11 May | 4 | Done
10 | Data layer development | Kestrel web dev |  | 20 Apr | 15 May | 0 | Done
11 | Tag manager build, development environment | Analytics team |  | 20 Apr | 15 May | 40 | Done
12 | Report suite configuration | Analytics team |  | 20 Apr | 24 Apr | 8 | Done
13 | Validation cycle 1, staging | Analytics team, Kestrel QA | Validation Report, cycle 1 | 22 May | 22 May | 12 | Done
14 | Fixes from cycle 1 | Analytics team, Kestrel web dev |  | 25 May | 28 May | 16 | Done
15 | Validation cycle 2, staging | Analytics team, Kestrel QA | Validation Report, cycle 2 | 29 May | 29 May | 10 | Done
16 | Fixes from cycle 2 | Analytics team, Kestrel web dev |  | 01 Jun | 03 Jun | 12 | Done
17 | Validation cycle 3, staging | Analytics team, Kestrel QA | Validation Report, cycle 3 | 04 Jun | 04 Jun | 8 | Done
18 | Publish to production | Analytics team |  | 11 Jun | 11 Jun | 4 | Not started
19 | Production check, one cycle | Analytics team, Kestrel QA | Production validation note | 12 Jun | 13 Jun | 8 | Not started
20 | Two starter Workspace projects and a handover session | Analytics team | Workspace projects, handover pack | 16 Jun | 18 Jun | 16 | Not started
21 | Phase 1 patch: sign out, form tracking, Named Day view | Analytics team, Kestrel web dev |  | 23 Jun | 30 Jun | 12 | Blocked
|  |  |  | Total hours |  | 246
Note on B3: What happens. One line, and it names an outcome rather than an activity where it can.
Note on C3: Who does it. Where two names appear, the first one owns it.
Note on D3: What exists at the end of it that did not exist before. Blank means it produces no artifact, which is fine, but a run of blanks is a warning.
Note on E3: Planned start.
Note on F3: Planned end.
Note on G3: Estimated hours. The total is what the project was sold on.
Note on H3: Not started, In progress, Done or Blocked.

## Assumptions
Assumptions and dependencies - the things that will move the date if they are not true
No | Assumption or dependency | Owner
A1 | The plan covers the website only. The applications are out of scope and are listed on the BRD Out of Scope sheet. | Analytics team
A2 | Data layer development is done by Kestrel web dev. Twenty working days are assigned. This is the single activity most likely to move the go live date, because nothing else can be tested until it exists. | Kestrel web dev
A3 | Three validation cycles on staging and one check on production. A fourth cycle would need a change request. | Analytics team, Kestrel QA
A4 | Kestrel QA provide a tester for each cycle. Validation with one person takes twice as long and finds less. | Kestrel QA
A5 | Staging behaves like production, including the payment gateway in test mode. A gateway that cannot fail on demand makes the payment failure solution untestable. | Kestrel web dev
A6 | Test data exists for the cases that are hard to produce: a failed payment, a discount code, a null search, an order with more than ten products. | Kestrel QA
A7 | Hours for meetings and administration are not in the plan and are logged separately. | Analytics team
A8 | Two Workspace projects and one handover session are included. Ongoing reporting support is not. | Analytics team
A9 | The form component is owned by a third party with its own release window. Any change to it is outside the dates in this plan. | Kestrel web dev
A10 | Consent must be answered before analytics fires. The consent tool and its categories are already live and are not being changed by this project. | Kestrel web dev